Terms of reference for working groups

If your steering committee decides to divide the work among smaller working groups, you may decide to agree ‘terms of reference’ for those groups. This will ensure participants understand what they are being asked to do and the limits to their powers. Set out below is an example that you may like to use as a model.

(Name)Parish Plan Steering Committee: Terms of reference for working groups

The purpose of each working group is to assist the parish plan steering committee (PPSC) to prepare an action plan for the community. Each working group will tackle a specific issue, or set of issues, or the needs and opportunities facing a specific group of people within the community.

Each working group should:

1. Clearly set out its purpose eg. “ to help young people (under 18 years) in the community identify their needs, ideas and concerns and to develop an action plan to meet these needs.”

2. Outline how it will gather information and carry out consultations.

3. Set out the timescale and estimated costs of gathering information and carrying out consultations.

4. Produce a short action plan setting out:

What is proposed?

Why the action is needed

Who will be responsible for taking the action?

When will the action be taken forward?

How the action will be implemented and how much it will cost?

5. The working group must be able to demonstrate that projects it has identified have the support of the local community and show that they have, where relevant, discussed projects with other organisations who will be able to assist in carrying out the action.

6. Each working group will appoint at least one, but preferably two members, to attend the regular PPSC meetings (those persons may already be members of the PPSC).

7. Each working group will be responsible for organising its own meetings and must provide a summary progress report to the PPSC meetings.

8. Financial expenditure in excess of £50 must be approved by the PPSC. Receipted expenses for reimbursement should be passed to the steering group treasurer on a monthly basis with reasons for the expenditure clearly given. PACK SECTION 4