Model Action Plan

| The Action (Community) | How it will be tackled | Priority | Timescales | Responsibility (Lead and partners) | Resource implications | Monitoring Responsibility |
| --- | --- | --- | --- | --- | --- | --- |
| Social |  |  |  |  |  |  |
| (1) Improvements to the village hall | Fix the roof Improve the leisure facilities | High | Initial meeting with partners in early Autumn. Work plan to be produced by October. Work to commence in Spring | Lead: Village Hall Committee Partners: The Parish Council, District Council may provide some funding. RCC halls’ adviser | Funding needed from a variety of sources to be determined with Village Hall adviser. Local builders and local grant- making trusts to be approached for resources and funding | Parish Plan Action Group to receive feedback from meetings |
| The Action (Service providers) | How it will be tackled | Priority | Timescales | Responsibility (Lead and partners) | Resource implications | Monitoring Responsibility |
| Environment |  |  |  |  |  |  |
| (2) Better maintenance of ditches, paths, hedges and verges | Regular clearance of ditches, cutting back undergrowth from paths and keeping hedges and verges trimmed | Medium | Short term – Refer concerns to Parish Council and District Council, ongoing maintenance. | Lead – The parish Council: District Council contractors | Suggestion to District Council to have work carried out by local contractor and managed by Parish Council | Environment group to refer the prioritised maintenance requests to the Parish Council and report via the Village magazine |
| The Action (Strategic) | How it will be tackled | Priority | Timescales | Responsibility (Lead and partners) | Resource implications | Monitoring Responsibility |
| Transport |  |  |  |  |  |  |
| (3) Review of traffic issues including parking, access to public transport and need for traffic calming | Research into links with Highways Dept at County Council, Local Transportation Service and Rural Transport Partnership. Ideas for review to include car share schemes, dial-a-ride, bus reroute and new cycle routes | High | Initial meeting with partners in early autumn. Long term timescale to be determined at meeting | Lead: Parish Chair to set up initial meeting Partners: Roles of RTP and local authority to be determined at the initial meeting | Long term implications unknown at this stage. Funding needed from a variety of sources, including the private sector. | Parish Council to monitor and report through Parish Magazine and standing item at Parish Council meetings |
| Economic |  |  |  |  |  |  |
| (4) Review of current tourism strategy | The initial work has been carried out to identify the key issues and opportunities relating to tourism potential and impacts. Identified needs include: Good quality leaflets, brown signs at bypass, more events and festivals, review of public toilet provision. | Medium | Long term: initial meeting of partners to be arranged late Summer | Lead: Council Tourism officer Partners: Parish Council, local authority, Development officer, Hidden Britain and the History and Heritage working group | Implementation costs costs unknown at this stage – council has agreed to cover the cost of plan production. | History and Heritage working group to monitor and report on progress through Village Magazine |